## IJB Actions
Todays Date = |  | 2025-06-26 14:29
Meeting Date | ID Number | Who Added | ACTION | Agenda Item | Status | Who is Actioning | B/F Date | Completion Date | Update (To be completed by Actioner) | Evidence/Rationale (To be completed by Actioner)
20.01.2022 | 1 | AM | Addressing Unmet Need in Social Care PJ will pick up a discussion with Vic McDade regarding staffing and notice periods, this will cover the Partnership, PJ will link with JG | 5 | Complete | PJ / NH |  |  | JW will ask for N Hamlet to link with NAH around her concerns re the Unmet Need in Social Care. Update 15.03.2023 - PJ confirmed this was complete she met with Jim Gatherum
23.06.2022 | 2 | AM | IJB Directions to Constituent Authorities A Short Life Working Group to progress annual directions to be formed Action: SLWG consisting of Chief Finance Officer, Director of Strategic Planning and Governance Officer has been set up and will take forward this work. First meeting to be held on the 13th October | 6 | Complete | DR / KK |  | 31.05.2023 | Update 23.03.2023 - KB has brought a report on IJB Directions, updates will come regularly
23.06.2022 | 3 | AM | Public Social Community Transport Project DR/NAH to meet to discuss funding proposals Public Social Community Transport Project WS asked for a report on what is happening in other areas | 13 | Complete | DR |  | 22.02.2024 | DR offered support to Third Sector to pursue Endowment Funding but this has not been progressed. Update 08.12.2022 - This action is sitting with the Community Planning Partnership, aspects of the H&SC Partnership which are not covered Update 23.03.2023 - JW / VW agreed to pick this up at the Community Planning Senior Leadership Team - These have both been shared with Richard Grieveson to add to agenda on 03.08.2023 Update 13.09.2023 - VW mentioned The endowment application was submitted outwith grant giving timescales and so was not approved by NHS Endowments committee. Discussions are taking place regarding approaches to Community Transport this is taking place through community planning structures. Update 29.11.2023 - VW confirmed A proposal to look at funding a post to explore how a social enterprise model of Community Transport could be taken forward in D&G has been prepared by Third Sector D&G and is being considered by NHS, Council and SOSE looking at 3 way split of funding. Further discussion on this will take place through Community Planning Senior Leadership Team structures. The NHS have agreed to provide their share of funding and confirmation from the other partners is awaited. Update 22.02.2024 - DR / VW confirmed this is now closed this is now included in the Local Outcome Improvement Plan (LOIP) which the Community Planning Partnership oversees.
18.11.2022 | 4 | AM | Minutes of the Previous Meeting LB asked for an update on the Workforce Summit, JW will link with Richard Grieveson regarding this. | 3 | Complete | VW / L Burgess |  | 10.04.2024 | This will take place on the 4th October, PJ to update the meeting if required Update 08.12.2022 – PJ confirmed an update following the summit will come back to IJB. Update 23.03.2023 - AM shared the Workforce Summit Report from October 2023, JW agreed for this to go via the Community Planning Leadership Group on 03.08.2023. VW and JW will be members of this CPSLT. Update 13.09.2023 - VW mentioned an action plan was developed following the summit and progress on this was reported to the Community Planning Senior Leadership team by the Employability, Skills and Partnership Manager, who would be happy to present to present to the IJB or relevant committee on this if helpful. Update 29.11.2023 - VW mentioned Lynne Burgess is supportive to attend an IJB and provide a presentation if in agreement? Update 07.12.2023 - PJ confirmed this can be shared to members and if any concerns this can be discussed Update 21.02.2024 - Lynn Burgess is attending the next Community Planning Partnership to provide a presentation and slides can be shared following it. Update 10.04.2024 - AM shared the presentation around members following the Community Partnership Meeting which Lynn Burgess attended
08.12.2022 | 5 | AM | Winter Update DR mentioned he has begun to map out the Annual Delivery Planning including all the Winter Plan Actions and to understand the impact of Winter on the delivery of our plans. The timeline is for a paper into the H&SC Leadership Group on the 19th of January 2023, The Strategic Plan Delivery and Commissioning Committee at the end of January 2023 and back to the IJB, meeting the March 2023. | 5 | Complete | DR |  | 31.05.2023 | Update 31.05.2023 - DR confirmed this update came via the ADP Report at the January IJB Strategic Planning and Delivery Committee
08.12.2022 | 6 | AM | PARTICIPATION AND ENGAGEMENT STRATEGY 2022 - 2025 NAH and LD discussed including people with lived experience, DR mentioned this is included in the document but worded in a different way, it is not the language usually used. RE will amend this. | 9 | Complete | RE |  | 24.03.2023 | Update 28.03.2023 - AC confirmed with Julie that amendments were made and this is now published on https://dghscp.co.uk/consultations/dghscp-engagement-strategy/
08.12.2022 | 7 | AM | THIRD SECTOR CONTRACTS DIRECTION NAH flagged will there be a consideration of the impact on inflation, and is the 7.7million the total amount spent by D&G Health and Social Care Partnership, DR will pick this up offline and feedback. JW confirmed that this is only the voluntary grants and does not include over £60M of spend with the Third Sector and the Independent Sector locally. | 12 | Complete | VG / NAH |  |  | Update 05.04.2023 - The HSCP currently spent £7.7m commissioning care and support delivered by third sector organisations last year. Each year, as part of the budget setting process, currently underway, consideration is given to implementing an uplift for all commissioned services, including these third sector partners. Increasing demand, workforce and financial challenges, including the increasing cost of living and inflation, are well documented and recognised as the main drivers to the need to deliver care and support differently. Working towards the IJB model of care should help shift the balance of care and contribute to addressing the current challenges. Update 18.05.2023 - VG took a paper to the Monthly Formal HSCLG where members approved the Option 3 – uplift applied to provider partners ‘not in scope’ based on Scottish Government Adult Social Care Pay Uplift rates of 2.73% or 3.3%
23.03.2023 | 8 | AM | INTEGRATION JOINT BOARD DIRECTIONS UPDATE To be added to Rolling Agenda for an update Quarterly | 7 | Complete | AM |  | 28.03.2023 | Update 28.03.2023 - AM added to Rolling Agenda Matrix
23.03.2023 | 9 | AM | IJB COMMITTEE SCHEME OF DELEGATION AND COMMITTEE UPDATE Members supported this approach, JG raised a concern regarding the Independent Sector involvement, KB / AM will pick this up and refresh all Terms of Reference. | 8 | Complete | AM / KB |  | 19.04.2023 | All Committee ToR have been approved via each committee, and can be requested via Amber Murray, these will be shared at the Induction Session on 20.04.2023
23.03.2023 | 10 | AM | SPECIFIC DUTIES REPORTS 2023 NAH asked in relation to Disibility, a report has been published for the employment gap. Within the Report it highlights that D&G is an outlier in terms of the percentage of people who have a disability and are in employment. NAH highlighted concerns that need to be addressed through all of our multi-agency planning structures. NAH will share this report with members. VW will also take this into the Short Life Working Group. KB will review where In-equalities should sit on the IJB Committee Structure. | 9 | Complete | AM / KB |  | 04.04.2023 | Update 24.03.2023 - AM shared Disability report which NAH highlighted with Members Update 04.04.2023 -In-equalities sits within the IJB Transformation, Innovation & Delivery Committee, as per rolling agenda
23.03.2023 | 11 | AM | UPDATE ON REVIEW OF MATERNITY SERVICES IN WIGTOWNSHIRE An update will come via the IJB Meeting on 26th April 2023. | 10 | Complete | AM |  | 24.03.2023 | Update 24.03.2023 - AM added this to the IJB Agenda on 26.04.2023as per VG update email
23.03.2023 | 12 | AM | RIGHT CARE RIGHT PLACE: INTERMEDIATE CARE Action: KDa asked in regards to the graph highlighting the Distribution of Age and questioned whether, with the Pandemic, a lot may have changed. KDa also asked if we had enough responses from the age group who don’t need care at the moment, it requires to be future proof. KDa requested for the language to be reviewed in terms of rehabilitation. GN will pick this up following the meeting, data has been taken pre pandemic. Action: JG asked within the Stage 2 part of the consultation, can we involve stakeholders and people with lived experience. JG also asked to meet up with individuals who are living in the care home sector currently to ascertain their views about potential future models. Action: VG will link with NAH outwith the meeting re the next stages of the process. | 12 | Complete | GN / GC / VG |  | 05.04.2023 | Update 05.04.2023: Action 1: VG confirmed they have plans to engage with younger people through the youth council and will make every effort to engage younger people. George will be able to feedback on the data question Action 2: VG confirmed they will engage with care home partners to facilitate a session or two with their residents Action 3: VG updated Third Sector Dumfries and Galloway have been involved in the planning of the consultation period. Their Health and Social Care Engagement Manager will join many of the consultation events, has had opportunity to influence the questions being asked during the consultation and as with the activities during the period of engagement will faciliate workshops within the Third Sector Update 05.04.2023: GN updated on the below We're currently going through the editorial process for the modelling report. David R has requested that we have a page turn review and this is being organised. The use of "rehabilitation" will be addressed during this editorial process. With respect to the data - COVID-19 did result in an increase in deaths across our population. The majority of deaths from COVID-19 occurred amongst older people, those aged 75 and over. This modelling has identified that it is people currently aged 55 to 64 years old that will be the biggest driver for increasing demand over the next 25 years. Therefore, it is considered unlikely that COVID-19 will substantively changed the results of this modelling.
26.04.2023 | 13 | AM | MEMBERSHIP UPDATE Membership of voting members were still to be agreed for: IJB Finance, Performance and Quality Committee IJB Transformation and Innovation Futures Committee | 6 | Complete | KB |  |  | Update 27.04.2023 - KB emailed all Voting members to seek further nominations for the vacant posts on the Committees
26.04.2023 | 14 | AM | MATERNITY SERVICES UPDATE MK suggested given the Independent chairs and expert will be stepping down once the preferred option is identified, it would be beneficial for the Independent Team to attend an IJB prior to this to highlight the process. DR will pick up a conversation with the Commissioning Team regarding this approach. | 9 | Complete | DR |  | 07.12.2023 | Update 31.05.2023 - This will come back to a future IJB inviting the Independence Chairs Update 22.06.2023 - JW confirmed this will come to the next IJB following this going into the IJB Strategic Planning and Delivery Committee. Update 27.09.2023 - L Boyce attended and gave a further update on the Maternity Service Update following the IJB Transformation, Innovation and Futures Committee in August - Kirsty Bell has closed off the Extant Direction which was previously issued.
22.06.2023 | 15 | AM | MINUTES OF THE PREVIOUS MEETINGS Discussion took place regarding the Chairmanship of the IJB Finance, Performance and Quality Committee. It was agreed that, according to the Scheme of Delegation, the Chair should have rotated to the Local Authority due to the previous Chair having covered a 2 year tenure. It was agreed that, subject to confirmation from Governance, Andy McFarlane would assume the role of Chair for the next 2 year period. | 3 | Complete | AM |  | 05.09.2023 | Update 22.06.2023 - This will be updated at the IJB Finance, Performance and Quality Committee on 5th July Update 05.09.2023 - AM / KB Joined the pre meet for the IJB Finance, Performance and Quality Committee, no one joined, KB will complete a membership update for the next committee on 12th Oct, Highlighting the Chair / Voting Members, this committee should have 6 Voting members and not only 4 like the others.
22.06.2023 | 16 | AM | DIRECTIONS PERFORMANCE UPDATE Governance Arrangements to be reviewed and shared around all the Bodies, including the Social Work Committee. | 7 | Complete | JW / KB |  | 05.03.2024 | Update 12.09.2023 - New Governance procedure will be presented as an appendix within the Direction Paper at the next IJB in September. KB will meet with S Morgan re the Social Work Committee arrangements Update 28.11.2023 - AM to schedule a meeting with Kirsty, Julie, Vlad, Stephen & Rebecca to review the new procedure developed - scheduled for 22.12.2023 Update 05.01.2024 - This meeting in december was cancelled and has been rescheduled for 22.01.2024 Update 05.03.2024 - KB confirmed she has attended Social Work Committee and went through the New Procedure and Associated Performance Report.
22.06.2023 | 17 | AM | DUMFRIES AND GALLOWAY ALCOHOL AND DRUG PARTNERSHIP STRATEGY AND DELIVERY PLAN 2023 – 2026 A question was asked by AF regarding the governance arrangements for the ADP and the role of the IJB in approving the Strategy (as the Strategic Commissioning Body). AA gave assurance that although the Governance Routes around the Alcohol and Drug Partnership had been confused, the performance framework has been completed highlighting the routes, and this will come back to a future IJB Meeting. | 10 | Complete | VW / AA |  | 05.03.2024 | Update 07.12.2023 - Workshop has been scheduled for 06.02.2024 feedback will be given at the March IJB Update 21.02.2024 - Workshop completed on the 06.02.2024, hosted by Penny Halliday, George Noakes and Jacqueline Stewart. Workshop began with a presentation regarding what the ADP is, current priorities, key challenges and achievements. Workshop ended with a presentation regarding the Performance Management Framework, highlighting ADP governance routes and reporting frameworks. Workshop was well attended and included question and answer segments.
22.06.2023 | 18 | AM | DUMFRIES AND GALLOWAY ALCOHOL AND DRUG PARTNERSHIP STRATEGY AND DELIVERY PLAN 2023 – 2026 Members agreed for the ADP Update to go via the IJB Transformation, and Innovation Futures Committee, prior to returning to the IJB, AM will amend the Rolling Agenda Matrix. | 10 | Complete | AM |  | 22.06.2023 | Update 22.06.2023 - AM added to the Agenda for the committee on the 10th Aug and linked with the appropriate colleagues.
22.06.2023 | 19 | AM | DUMFRIES AND GALLOWAY ALCOHOL AND DRUG PARTNERSHIP SELF ASSESSMENT JW suggested arranging a workshop for IJB Members around the Alcohol and Drug Partnership, VW and SM will discuss this with the Alcohol and Drug Partnership, and feedback re a date. | 11 | Complete | VW / SM |  | Complete | Update 13.09.2023 - G Noakes / J Davies developing the ADP Performance and Governance Framework, and keen to take IJB Members through as a workshop session beginning of 2024. AM will link with the appropriate and schedule date, inviting Penny Halliday as ADP Chair. Update 28.11.2023 - AM linked with G Noakes, P Halliday and J Davies re a 1.5hr Workshop session for February 2024, ageed to schedule on the 6th Feb 2023, diary invite has been issued
27.09.2023 | 20 | AM | IJB Committee Meetings Meeting to be scheduled in the New Year for Committee Chairs / Leads in terms of Committee Structures | 5c | Complete | AM |  | 05.01.2024 | Update 07.12.2023 - AM still to schedule Update 05.01.2024 - Meeting scheduled for Thurs 25th January 2024
27.09.2023 | 21 | AM | RIGHT CARE RIGHT PLACE, INTERMEDIATE CARE JG also mentioned a number of the points raised, are National concerns not only Locally, but this will affect Care Homes locally the pressure on staff at the moment is significant. JG asked for us to undertake a review of all Care Homes, to support this piece of work, there is a number of assumptions within the report but no Care Home Operational intelligence, DR and VG will pick this up out with the meeting with JG. | 8 | Complete | DR / VG |  | Complete | Update 28.11.2023 - VG / DR met with J Gatherum - and the IJB Issued a Direction for us to undertake a review of the role of Care Homes in the longer term.
27.09.2023 | 22 | AM | RIGHT CARE RIGHT PLACE, INTERMEDIATE CARE AMcF discussed with DR in terms of an email received regarding Kirkcudbright Hospital, DR will link with the individual with answers to the questions. | 8 | Complete | DR |  | 29.09.2023 | Update 28.11.2023 - DR confirmed letter was issued 29.09.2023
07.12.2023 | 23 | AM | 2024 IJB MEETING / IJB COMMITTEE DATES / STRATEGIC PLANNING GROUP The IJB agreed to schedule an additional session in April to look at the Budget process, this has been similar to previous years, AM will schedule for April 2024 and in future years this will be a standalone meeting. | 5 | Complete | AM |  | 12.12.2023 | Update 12.12.2023 - Extra meeting on the budget scheduled and in diaries for 16.04.2024
07.12.2023 | 24 | AM | MEMBERSHIP UPDATE Previously there were six members on the IJB Finance, Performance and Quality Committee, but four on other Committees. It was deemed previously to have the IJB Chair and Vice Chair and four additional members. KB will pick this up offline and will come back with an update. | 6 | Complete | AW |  | 16.04.2024 | Update 21.02.2024 - Alison will provide a report via the committee update. Update 16.04.2024 - AW has linked with AMcF / KD as Chair and Vice Chair and will bring a formal update to the September IJB
07.12.2023 | 25 | AM | INTEGRATION JOINT BOARD COMMITTEE UPDATES IJB Committee Updates from Chairs - IJB Audit Risk and Governance KB highlighted a risk workshop will be scheduled in the New Year. IJB Members must take ownership of the IJB risks so as to understand the impact of decisions / directions being issued where the subject experts will also be around the table. | 7 | Complete | AM / KB |  | 18.01.2024 | Update 18.01.2024 - Risk workshop has been arranged on the 22.02.2024 following the IJB Audit, Risk and Governance Committee - K Harper will lead on this, invite has been shared.
05.03.2024 | 26 | AM | INTEGRATION JOINT BOARD COMMITTEE UPDATES Action: AW is completing a refresh of all committee Terms of Reference, and these will be shared via the next committee updates in June. | 5 | Complete | AW |  | 16.04.2024
05.03.2024 | 27 | AM | FINANCIAL PERFORMANCE UPDATE – QUARTER THREE Members discussed an agreed for a workshop to be held for IJB Members, where KK to take members through a wider presentation, this could be arranged following the IJB Finance, Performance & Quality Committee on April 9 2024. Action: AM will arrange to get this invite issued. | 6 | Complete | AM |  | 06.03.2024
05.03.2024 | 28 | AM | DIRECTION PERFORMANCE UPDATE Action: KB suggested at the next IJB in June 2024, an opportunity to go through each individual direction. Action: Members requested for the Directions to be in the public domain, KB is supportive to look into this. | 7 | Complete | KB |  |  | Update 04.06.2024 - KB attended and provided a full overview / presentation on Directions, with a number of actions noted and a further amendment to come to the September IJB. AM to schedule a meeting with N Hamlet, S Morgan and A MacFarlane re Statutory Guidance - This was held on Tues 20th August Update 24.09.2024 - KB provided a full presentation and overview of ALL directions and an update comes to all IJBs.
05.03.2024 | 29 | AM | RIGHT CARE RIGHT PLACE COTTAGE HOSPITALS Action: Care and Repair Housing funding was approved at Full Council, and AMcF asked is this included in the Housing Review. GS chairs the Care and Repair Steering Group, where this Grant has been granted, this can run alongside Right Care Right Place, a report setting out this summary position will come back. | 8 | Complete | GS |  |  | Update 10.04.2024 - AM emailed GS for an update on the action noted confirming when something will come back. Update 22.05.2024 - GS confirmed a meeting is due to be scheduled in regards to Housing with Care and Support to review roles and responsibiliies. Report on Care and Repair for Community Health and Social Care will come back to the next meeting, following going through CH&SC Directorate Meeting first. Update 29.08.2024 - Agreed with GS a report must come back to IJB in terms of Housing etc... Update 24.09..2024 - GS attended and provided a presentation in terms of housing.
24.09.2024 | 30 | AM | MEMBERSHIP UPDATE Action: L Dorward approved me the Vice Chair on the IJB Strategic Planning, Delivery and Commissioning Committee and also to be the Rep on the Public Health Committee. | 6 | Complete | AM |  |  | Update 17.10.2024 - LD attended an intro session with KB / AM was provided all paperwork and was welcomed at the committee as Vice Chair in November
24.09.2024 | 31 | AM | FINANCIAL PERFORMANCE UPDATE – QUARTER ONE Action: Financial Recovery Sessions have been held with staff members, no messaging / updates with the member of the public, however this is a key focus to ensure Public Messaging. | 9 | Complete | KK |  |  | Update 15.10.2024 - KK met with Comms lead to review actions from staff engagement sessions and plan to have a updated comms plan developed as part of the budget setting process for 25/26, further updates will be presented as part of the regular IJB finance updates. Update 17.12.2024 - Comms was issued.
17.12.2024 | 32 | AM | IJB Strategic Planning Delivery & Commissioning (meeting 14.11.2024) Action: Members agreed the update in terms of the Direction on commissioning a supported accommodation unit and staff base at the Garrick Development, KB will develop this Direction and issue it to both parties. | 5c | Complete | KB
17.12.2024 | 33 | AM | IJB Transformation, Innovation and Futures (meeting 13.08.2024 and 12.11.2024) Action: As part of the update a Direction is attached on Retaining Galloway Community Hospital at the heart of acute service delivery for people in Wigtownshire. KB will arrange for this to be issued. | 5d | Complete | KB
17.12.2024 | 34 | AM | IJB DIRECTION PROGRESS UPDATE Action: IC mentioned in terms of the Palliative Care Strategy, KB is taking this through the IJB Finance, Quality and Performance Committee, as we have had this strategy in place. The Palliative Care Strategy should come via the IJB Strategic Planning Delivery & Commissioning, which KB will arrange for this to go to the January committee. | 6 | Complete | KB |  |  | Update 10.01.2025 - AM shared the Palliative Care Strategy with the IJB S,P & D Committee due to take place on 21.01.2025
17.12.2024 | 35 | AM | BEST VALUE STATEMENT / DRAFT RISK MANAGEMENT STRATEGY Action: AMcF mentioned in terms of Page 5, we must highlight in more detail including some examples in terms of the details. KK confirmed this is due to be refreshed for 2024 / 2025 and asked for all IJB Members to be part of this, possibly include as a standing item on all the committees. | 7 | Complete | KB |  |  | Update 22.01.2025 - AM issued an example to Chairs and Leads, confirming a deadline for completion of 16.05.2025 - for this to go to the June IJB A, R & Gov Committee Update 04.03.2025 - Agreed this will go via IJB A, R & G committee in June, AM re shared round key members
17.12.2024 | 36 | AM | FINANCIAL PERFORMANCE UPDATE – QUARTER TWO Action: NHS Budget Letter was discussed and will be shared with members following the meeting. Our position will increase, KK highlighted the detail within the letter, this will not be worked up for the IJB Finance, Quality and Performance Committee in January, and a workshop will be scheduled to look into the budget in February prior to the IJB in March. |  | Complete | AM |  |  | Update 17.12.2024 - Workshop has been scheduled for all IJB Members on Tues 18th February 2025.
04.03.2025 | 37 | AM | IJB DIRECTION PROGRESS UPDATE – NEW DRAFT DIRECTIONS Action: KB mentioned scheduling another workshop in terms of capturing Impact Assessments / Financial Risks. Action: Strategic Commissioning Intentions to be included / matched in new template. Action: Template to go to Senior Leadership Team for Council and Board Management Team, AM will link KB into the appropriate agendas. Action: VK has asked for a discussion out with regarding the update in the report about staffing within Acorn House. Action: CH asked when the report will come back around Acorn House and will NDAS be part of this update. KB confirmed impacts and implementations have been highlighted and will be part of the report. | 6 | Complete | KB |  |  | Update 14.03.2025 - KB will take Direction Update / Template to the 12th May SLT then 14th May BMT - all agreed.
04.03.2025 | 38 | AM | MEMBERSHIP UPDATE Action: KB / AM will do a piece of work in terms of the Chairs / Vice Chairs / Members within the IJB Committees and will confirm with them. This will be a formal membership update at the extraordinary meeting on the 15th April 2025. KB will link with Local Authority too in terms of new Council Members. | 7 | Complete | KB / AM |  | 15.04.2025
04.03.2025 | 39 | AM | FINANCIAL PERFORMANCE UPDATE – QUARTER THREE Action: Further IJB Financial Workshop will be held within the IJB Finance, Performance & Quality Committee on the 8th April, Invite will be extended to all IJB Members. | 8 | Complete | KK / AM |  | 13.03.2025 | Update 13.03.2025 - Invite for the 8th April was shared to all IJB Members.
03.06.2025 | 40 | AM | INTEGRATION JOINT BOARD COMMITTEE UPDATES Action: DR highlighted following the committee update on Strategic Decisions the Committee agreed to propose that IJB Members participate in a workshop in August 2025 to explore these pathways and hear people’s experiences with a view to agreeing a Direction to redefine how we provide support to those in greatest need, members approved to schedule this workshop. | 5 | Complete | AM |  | 06.06.2025 | Update 06.06.2025 - IJB in September extended to host the Strategic Decisions workshop
03.06.2025 | 41 | AM | MEMBERSHIP UPDATE Action: Press release due to be issued over the next day or two regarding the recruitment of the Service and Carers Representation, KDa confirmed the importance of this process. | 6 | Complete | KB / RE |  | 12.06.2025 | Update 12.06.2025 - KB completed adverts and issued to RE for publishing, KD was copied in for info.
03.06.2025 | 42 | AM | IJB DIRECTION PROGRESS Action: Annual Performance Report will come to the next meeting which will be all the outstanding directions including Health and Wellbeing outcomes. | 7 | Ongoing | KB | 23.09.2025
03.06.2025 | 43 | AM | FINANCIAL PLAN UPDATE 2025/26 Action: NH raised the importance for the IJB to be appraised of the Social Work Savings that the Deputy Chief Operating Officer is leading on – Gareth Marr is to be invited to the next scheduled Finance, Performance and Quality Committee to provide an update. | 10 | Complete | AM |  | 12.06.2025 | Update 12.06.2025 - AM shared invite with Gareth and this will be picked up at the
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
219
220
221
222
223
224
225
227
228
229
230
231
232
233
234
235
236
237
238
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
268
269
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
288
289
290
291
292
293
294
295
296
297
298
299
300
306
307
308
311
312
313
314
315
316
317
318
319
320
321
322
325
326
327
328
329
340
341
342
343
344
345
345
346
347
348
349
350
351
352
353
354
359
363
364
366
367
375
376
384
385
386
387
388
389
390
391
392
393
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
424
428
426
427
428
429
430
431
432
433

## Audit, Risk & Governance Action
Todays Date = |  | 2025-06-26 14:29
Meeting Date | ID Number | Who Added | ACTION | Agenda Item | Status | Who is Actioning | B/F Date | Completion Date | Update (To be completed by Actioner) | Evidence/Rationale (To be completed by Actioner)
11.03.2021 | 1 | AM | UPDATE TERMS OF REFERENCE – MEMBERSHIP AW to share the Scheme of Delegation with Members for review. AW to amend the Frontis to show those Members whose attendance is required. AW to send LB links to documentation pertaining to this Committee | 10 | Complete | AW |  | 23.02.2023 | Ongoing - The Scheme of Delegation has been shared with all Members of the IJB, comments are due back by the 30th June to allow for fuller review in line with other strategic documentation. An update to the Frontis has been undertaken following confirmation of membership at the IJB on the 27th May 2021. LB is now in receipt of relevant documentation. Update 08/06/2021 this has been postponed to the September meeting to allow for appropriate scrutiny of Scheme of Delegation. Draft Scheme of Delegation coming to 23rd Feb 2023 meeting. Update 16.11.2023 - Draft Risk Strategy being presented to November meeting.
09.09.2021 | 2 | AM | Risk Management Quarterly Progress Report LB queried whether the risk templates used at IJB A&R could be used for other IJB Committees, KK highlighted this would be helpful and will look into this offline. | 6 | Complete | KK |  |  | Update 23.02.2023 - KK highlighted the continued absence of the IJB’s Governance Officer who is responsible for Risk Management for the IJB. No progress has been made on this in recent months, but the IJB’s Corporate Risk Register will be reviewed at Health and Social Care Leadership Team in the coming weeks. Update 08.06.2023 - Risk Strategy added to agenda for September meeting
09.09.2021 | 3 | AM | Internal Audit Update MC requested that JWa and KK meet to map through Audit Committee processes across the partnership. | 7 | Complete | KK / Jwa |  | 08.06.2023 | Update 23.02.2023 - JWa noted that she is meeting with the Internal Audit team within the Council to progress this within the coming weeks. Update 23.02.2023 - JWa noted that she is meeting with the Internal Audit team within the Council to progress this within the coming weeks. Update 25/5/23 - JWa has met with the Council Audit Manager to discuss joint audit reporting arrangements. This was previously brought to ARC in March 2022 and is attached to the audit update at the June 2023 meeting.
09.09.2021 | 4 | AM | IJB Corporate Risk Register Members agreed for an update paper on Risk Management to be presented to the IJB in November 2021. The report will also be shared to IJB A&R members virtually. | 9 | Complete | KK / AW |  |  | Outstanding due to work pressures. Risk register needs further review and discussion at Health and Social Care Governance and Performance Group. Need to confirm with Chair and Chief Officer around risk reporting and how this feeds into new governance arrangements. Remains outstanding. Update 08.06.2023 - Risk Strategy added to agenda for September meeting. Update 16.11.2023 - Draft Risk Strategy being presented to November meeting.
23.02.2023 | 5 | KM | Terms of Reference IJB Audit, Risk and Governance Committee GB noted that section 2.3 states the Committee will "recommend approval of the Risk Management Strategy", but not who will develop this. KK highlighted that this will be developed by relevant Officers who will submit their strategy to the Committee for approval. GB requested that the language around this be strengthened to highlight the scrutiny role this Committee will have. | 5 | Complete | KK
23.02.2023 | 6 | KM | Internal Audit Update JWa noted she is meeting with the Council's Audit Manager within the next few weeks to fully understand the epxectations of what will be achieved within the 2022/23 Audit Plan by the Local Authority, and to begin planning for 2023/24. KD requested that any update provided by the Audit Manager on potential delays within the Local Authority's planning structure be reported back to IJB ARG prior to the next meeting. | 8 | Complete | JWa |  | 08.06.2023 | Update 25/5/23 - JWa has met with Council's Interim Audit Manager to discuss plan progress. There have been positive discussions around sharing of information and closer working arrangements. Any delays will have minimal impact to the reporting through to the IJB AR&G Committee.
23.02.2023 | 7 | KM | Internal Audit Update GB requested that JWa provides opinion at a future meeting of how the other IJB committees are performing within their new remits. | 8 | Complete | JWa |  | 08.06.2023 | Update 25/5/23 - JWa has attended one of each of the new meetings and will provide feedback at a later stage once the new structure is more settled.
08.06.2023 | 8 | KM | Draft Annual Report and Accounts 2022/23 KK highlighted that ths sequencing of the preparation of the IJB accounts, being reliant on both NHS and Council accounts being prepared, has resulted in the IJB accounts running to a slightly later timescale. KK to look at planning the June 2024 meeting slightly later | 5 | Complete | KK/KM |  |  | Update 30/11/2023 - 2024 meeting schedule amended to make this meeting later in the year
08.06.2023 | 9 | KM | Draft Annual Report and Accounts 2022/23 GB queried whether there can be a summary version issued as part of the public consultation for future years, given the complexity of the document. KK advised she will consider this as part of the accounts process for next year but noted the IJB Accounts are much simpler than the NHS and Council Accounts. | 5 | Complete | KK |  |  | Noted that this would be looked into as part of the Annual Accounts development process for 2024/25
08.06.2023 | 10 | KM | Internal Audit Quarterly Report Members agreed to host a meeting of the Audit Committee Chairs and Heads of Audit from the Council, IJB and NHS. | 7 | Complete | KM/JWa |  | 2023-07-31 | Update 06/09/2023 - Meeting held 04/09/2023. Follow up session to be arranged for November 2023.
08.06.2023 | 11 | KM | Governance Update GB requested that Environmental considerations be added into the monitoring process for Directions | 10 | Complete | KB |  |  | Update 06/09/2023 - KB noted that the template had been adjusted to include environmental considerations
14.09.2023 | 12 | KM | NHS Audit & Risk Committee Annual Assurance Statement Kda requested that GM seek clarity on whether the Local Authority has an equivalent Annual Assurance Report and Statement for their Audit, Risk and Scrutiny Committee | 5 | Complete | GM |  |  | Added to AOCB of September 2024 meeting
30.11.2023 | 13 | KM | Chief Social Work Officer Annual Report KK noted that this report should be presented to the next available meeting of the IJB, highlighting that although this report has had visibility within the Council and at this Committee, it would be beneficial for the IJB to review. | 5 | Complete | RA
30.11.2023 | 14 | KM | Internal Audit Quarterly Update KK noted that there has been a recent Social Work audit around processes and procedures which would be good for Jwa to highlight to the next meeting. Further noted that Richard Fox would be invited to attend the next meeting to update on Council audits in JWa's absence. | 7 | Complete | JWa
28.06.2024 | 15 | KM | Draft Annual Report and Accounts 2023/24 Original timing of this Committee proved too difficult to meet the deadline for pulling together the accounts, due to conflicting timescales with the NHS Annual Accounts process. KK requested that the Committee be scheduled for around the end of June 2025. | 6 | Complete | KB |  |  | Update 24.12.2024 - KK agreed no progression on this
28.06.2024 | 16 | KM | Draft Annual Report and Accounts 2023/24 GB noted that the section on inspection of care homes noted the grades given as part of each inspection, but does not contain a narrative around work ongoing to improve that grade. NH requested that a note be added in around the role of the Care Home Collabroative Group. KK noted that this would be added in. | 6 | Complete | KK |  |  | Added to accounts - propose to close Update 24.12.2024 - KK agreed was actioned in accounts which were signed off in September
28.06.2024 | 17 | KM | Chief Finance Officer Update KK noted that at the most recent meeting of the IJB Chief Finance Officer network they had an update on the progress with the National Care Service and the work that's happening to progress it. As the consultation around this develops, KK agreed to plan an IJB workshop around this over the next few months, linking with KB and NH. | 9 | Complete | KK/KB/NH |  | 25.02.2025 | Update 25.02.2025 - KK highlighted this has now been stood down so no requirement for a workshop, in the current timeframe nothing is due to happen.
17.09.2024 | 18 | AM | Membership Action: KK highlighted that IJB Audit, Risk and Governance Committee was short a council voting member and requested that KB look at this for future meetings. KB noted that a membership update would be presented to the IJB with the aim of addressing all committee vacancies. | 4 | Ongoing | KB |  |  | Update 25.02.2025 - Ongoing challenges around this and this will be picked up at the next committee due to the change in IJB chair. Update 03.06.2025 - KB held a workshop with IJB Members in regards to the Scheme of Delegation and the review of the committees themselves, which this action is part of. Update 24.06.2025 - Action was flagged within the Scheme of Delegation Update regarding the chair for this committee, KB / AM will work on this with Council / NHS Members
17.09.2024 | 19 | AM | Internal Audit Report – Care and Support at Home Action: This audit will be followed up on in around 6 months time in line with Council internal audit practice, a follow up report to be brought back to IJB Audit, Risk and Governance Committee following these findings. | 10 | Ongoing | RF | 16.09.2025 |  | Update 24.12.2024 - AM emailed RF for an update Update 06.01.2025 - RF confirmed follow-up in June, together with another audit report Update 25.02.2025 - This will come back via R Fox at the next meeting in June. Update 20.06.2025 - RF confirmed he will bring update in September.
25.02.2025 | 20 | AM | Chief Finance Officer Role Action: Proposal that an update in terms of the CFO role be brought back to the Special IJB in April, KK will link with NH. | 5 | Ongoing | KK |  |  | Update 03.04.2025 - This is due to go within the Membership update to the IJB on 15th April 2025, and then will be brought to the June Committee Update 16.06.2025 - KK confirmed Update provided at 3 June 2025 IJB, will provide further verbal update at Committee on 24th June. Update 24.06.2025 - Job Description is due to go out, and an Interim is being recruited at the moment from Agency, Gareth Marr is arranging the recruitment process.
25.02.2025 | 21 | AM | Chief Internal Auditor Quarterly Update February 2025 Action: JW asked in terms of the replacement of the chair for this committee, that a further meeting of the Audit and Risk Committee Chairs across NHS, Council and IJB should be arranged. | 6 | Complete | JWa |  | 24.06.2025 | Update 03.04.2025 - AM emailed for an update on the action / bring forward
25.02.2025 | 22 | AM | Governance Update Action: KD will link with KB / NH in terms of streamlining the committees, IC agreed in terms of this discussion, Self evaluation is a key process and could lead to more streamline / less committees. | 7 | Complete | KD / KB |  | 24.06.2025 | Update 03.04.2025 - AM emailed for an update on the action / bring forward Update 16.06.2025 - As per update in Action 15.
24.06.2025 | 23 | AM | Chief Internal Auditor Quarterly Update – June 2025 Action: Members agreed and requested for a review in terms of the Data Sharing Direction, AM will link with KB out-with to arrange this. Action: KK also agreed to review the Risk Register and provide an update back to the next committee. | 6 | Ongoing | KB | 16.09.2025
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
219
220
221
222
223
224
225
227
228
229
230
231
232
233
234
235
236
237
238
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
268
269
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
288
289
290
291
292
293
294
295
296
297
298
299
300
306
307
308
311
312
313
314
315
316
317
318
319
320
321
322
325
326
327
328
329
340
341
342
343
344
345
345
346
347
348
349
350
351
352
353
354
359
363
364
366
367
375
376
384
385
386
387
388
389
390
391
392
393
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
424
428
426
427
428
429
430
431
432
433
30.11.2023

## Finance, Performance & Quality
Todays Date = |  | 2025-06-26 14:29
Meeting Date | ID Number | Who Added | ACTION | Agenda Item | Status | Who is Actioning | B/F Date | Completion Date | Update (To be completed by Actioner) | Evidence/Rationale (To be completed by Actioner)
13.10.2022 | 1 | AM | Minute of the Meeting of the 24th March 2022 AW will share these minutes round the Voting Members from the IJB Performance and Finance Committee for formal approval. | 3 | Complete | AW |  | 13.10.2022
13.10.2022 | 2 | AM | Committee Terms of Reference A Workshop will be held on Thursday 17th November to discuss the new committee Terms of References. A diary invite will be issued to members. | 5 | Complete | AM |  | 20.12.2022 | Workshop was held on 20th December 2022 Update 13.04.2023 - Final version was approved.
13.10.2022 | 3 | AM | Future Performance Reporting LD noted that a session on the Annual Delivery Plan (ADP) would benefit this committee, it was noted that DR and team could align the ADP with Directions issued to ensure appropriate oversight, and this was agreed by members. It was noted that the finance elements of these directions may not be available from day one (due to resource challenges as noted previously). It was agreed by the committee that this would be a very helpful starting point and we need to make sure that value is added through this process. | 9 | Complete | DR |  | 16.05.2023 | Update 16.05.2023 - DR confirmed this has been completed
13.04.2023 | 4 | AM | Draft Financial Plan and Budget for 2023 / 2024 CG will pick up a conversation offline in regards to more detail in terms of National Care Home Risks that are built in, we have a lot of potential movement. | 5 | Complete | KK / CG |  |  | Update 16.05.2023 - KK / CG confirmed: The risks in outline are that, if the current NCHC offer is not improved by TSG/Cosla or accepted by Scottish Care members, Care Homes may choose to: - Give notice on NCHC and current publicly funded placements, requiring to be paid at privately funded levels or going fully private. - Seek to collectively negotiate a local contract for public placements, at higher rates than NCHC - Seek hybrid individual arrangements, by Home or by resident - Close Home/s Clearly, all scenarios have increased associated cost pressures for DGHSCP and would bring considerable risks, complexity and uncertainty for placements and provision. In all scenarios, there are significant existing financial risks for Homes, with closure for some a real possibility this coming year. One recently shared details of a 520% increase in energy costs in the last year and several are sharing concern at the ending of the staff support fund and other covid mitigations, despite the costs of staff isolation etc still being there for employers. It’s unlikely any offer will be able to fully mitigate these kinds of pressures. I am not aware of any D&G Homes actively considering closure, but owners/Directors will also be awaiting national position before being able to make decisions. Update 05.07.2023 - CG confirmed this is complete
13.04.2023 | 5 | AM | Proposal for Annual Performance Report 2022 / 2023 AA and KB will be planning a workshop as part of the Induction Process, 3 functions of the IJB concept will be part of this. General Introduction is scheduled for Thursday 20th April, deeper dive following this induction will be shared. KB will be including Directions updates through this committee, following the paper she presented at the last IJB on 23rd March 2023. | 6 | Complete | AA / KB |  |  | Update - 24.04.2023: AM included Directions on the Rolling Agenda Matrix, and was also presented on the 22nd June at the IJB
13.04.2023 | 6 | AM | Contract Monitoring Update SW mentioned one of the asks today is to bring the Third Sector Contract Monitoring report to the next meeting and the Governance Structure will be brought to a meeting approx October 2023. AM will include these in the Rolling Agenda Matrix. | 7 | Complete | AM |  | 05.07.2023 | Update - 24.04.2023: AM included on the Rolling Agenda Matrix
13.04.2023 | 7 | AM | Short Break Service Update JW confirmed in terms of the next IJB there is a need for us to have an update in terms of the options being reviewed, and we could present the timeline we are working towards. JW stated that Elected Members and members of the public are asking about timelines and it is important that this work is transparent. | 9 | Complete | FP |  | 16.05.2023 | Update 16.05.2023 - This went to the Full IJB for an update and will go to the June IJB Update 05.07.2023 - An update will come forward to the IJB Transformation, Innovation and Future Committee on the 10th August 2023.
05.07.2023 | 8 | AM | Directions Performance Update Action: GG asked in terms of the column regarding the process of the Directions, could we include in the table a timescale, KB is in the process in completing this piece of work. | 6 | Complete | KB | 12.10.2023 | 23.08.2023 | Update 23.08.2023 - KB included another row on the template, this will confirmed at the next committee meeting
05.07.2023 | 9 | AM | Governance Structure for Contract Monitoring Action: CG highlighted as a provider they have a mixed economy, with a number of charities and social enterprises. VG mentioned essentially you have your registered and non registered providers and agreed that this language will be reflected through the structure. | 7 | Complete | VG |  | 09.01.2024 | Update 09.01.2024 - KB confirmed, the language used, and this has been completed
05.07.2023 | 10 | AM | Third Sector Contract Monitoring Report Action: DR mentioned this will be reflected in future reports, PT and VG will take the feedback and review the scale / scope of the risks. | 8 | Complete | PT / VG |  | 09.01.2024 | Update 09.01.2024 - PT attending today with an update
05.07.2023 | 11 | AM | IJB Annual Performance Report 2022 / 2023: First Draft Action: Highlights within the report include increase on Consultation and Engagement over the year, including Time to Talk, Right Care, Right Place and Maternity Service Review. The timetable with the final draft will go to another committee for approval. | 9 | Complete | GN / AA |  | 09.01.2024 | This report has been publlshed.
09.01.2024 | 12 | AM | Directions Performance Update Action: Update on the Mental Health Strategy to come to the IJB Transformation, Innovation and Future Committee in February then to the IJB to request a direction, AM will link with DR and J Murray for completion | 6 | Complete | KB / AM |  | 08.10.2024 | Update 09.04.2024 - NH will pick this up with JM at next 1:1 on 23.04.2024 Update 28.08.2024 - AM linked with KB / NH again for an update. Update 08.10.2024 - KB provided a verbal update in terms of closing a number of the Directions, a gap anaylsis is being developed.
09.04.2024 | 13 | AM | Directions Performance Update Action: AM to share round the presentation | 5 | Complete | AM |  | 26.04.2024 | Update 26.04.2024 - AM shared presentation round members.
09.04.2024 | 14 | AM | Directions Performance Update Action: AMcF asked in regards to the diagram shared, should a number of the arrows be amended, DM mentioned the routes for issuing the directions is missing and will be added in terms of the routes down through the Partnership. Action: The council committee reporting process has changed, and AF mentioned was this completed prior to the new process, this will be amended to suit. | 5 | Complete | DM |  | 01.05.2024 | Update 01.05.2024 - KB and A Allan have been meeting and amended the diagram and will co-ordinate D&G Council.
09.04.2024 | 15 | AM | Quarterly Community Planning Partnership Performance Update Action: AM / KB will pick up a discussion with V White in terms of reporting through this Committee. V White was not in attendance today. | 6 | Complete | AMcF / VW |  | 08.10.2024 | Update 09.07.2024 - Discussion was had at the last IJB, VW to link with AMcF - email will email again. Update 28.08.2024 - AM linked with H Wood again for an updat in terms of the meeting/ reporting. Update 17.09.2024- VW confirmed she has met with AMcF and he agreed that as he is the IJB rep on the CPP Board it would be for Andy to provide relevant updates to the IJB
09.04.2024 | 16 | AM | Contract Monitoring Report: Care Home Action: DR / PT will pick up a discussion offline in terms of an anonymous RAG Status which will allow members to see the changes. | 7 | Complete | DR |  | 26.06.2024 | Update 26.06.2024 - DR confirmed report coming to July meeting demonstrates the change over time.
09.04.2024 | 17 | AM | Committee Membership / Terms of Reference Action: Previously back in 2016 this committee had 6 Voting Members, including the IJB Chair / Vice Chair, but we currently do not have the capacity in our Membership for 6 Voting Members, so will reduce this to 4 Voting Members, but to include Kim Dams as Vice Chair. AMcF agreed for AW to link with K Dams / members. Action: AW highlighted that the Service Rep is included in all the committees, but no Carers Rep, members agreed for this to be amended within the Terms of Reference and the Standing Orders include the in-committee sessions and links together with the Terms of Reference for each committee. | 8 | Complete | AW | 24.09.2024 | 29.04.2024 | Update 29.04.2024 - The reduction in membership wasn't around capacity it was to reduce the voting members in line with the other committees who all have 4. Both Andy and Kim will as Chair and Vice Chair of the IJB be Chair and Vice Chair of this Committee. I have written to them both separately to advise who the other member from each of the constituent parties will be (1 from NHS and 1 from Council). Regarding Carers Rep inclusion this is in hand. A report will come to the IJB in September, as the Audit, Risk and Governance Committee is after the next IJB and that committee hasn't signed off on their Terms of Reference yet.
09.07.2024 | 18 | AM | Any Other Business Quality Updates AMcF mentioned we have no Local Authority Advisors on this group, input from Social Work would be beneficial for this group. |  | Complete | KB |  | 08.10.2024 | Update 28.08.2024 - AM linked with KB again for an update. Update 08.10.2024 - AMcF confirmed he will link with S Morgan in terms of inviting a deputy.
07.01.2025 | 19 | AM | Welcome, Introduction and Apologies Action: NH will link with Dawn Roberts in terms of Council Voting Members, and KB will link with Governance again from Council. |  | Complete | KB / NH |  | 15.04.2025 | Update 20.01.2025 - AM emailed both NH / KB in terms of the action and for an update. Update 21.01.2025 - Both NH and KB have reached out today, to Dawn Roberts and Vlad in terms of Governance, and will link re the feedback Update 27.03.2025 - Council have confirmed our new Local Authority Voting Member is Richard Brodie - AM reached out welcoming him formally on the 15th April at the IJB and will be invited to future meetings.
07.01.2025 | 20 | AM | Contracts Monitoring Update Third Sector Action:DR mentioned in terms of sharing intelligence, Scottish Care attends quarterly to provide an update and the triangulation is important. This is being explored within Third Sector, Contract Management Team Table to include Third Sector and Scottish Care, PT will pick this up. |  | Complete | PT |  | 23.06.2025 | Update 20.01.2025 - PT confirmed it was discussed at the CMG on 14th January. While there was agreement that it would be good to have external stakeholders involved in CMG, there was no final decision as to the format this would take so there is to be further discussion and agreement to be sought at the February meeting. Update 27.03.2025 - PT confirmed this is deferred to the May CMG and will come back as a further update. Update 16.06.2025 - PT confirmed discussions are still ongoing regarding this, alongside a wider discussion on the format of CMG meetings going forward. It is expected to be discussed at the next CMG meeting on 1st July. Update 23.06.2025 - VG confirmed this is complete and Third Sector and Scottish Care will attend the CMG on 1st July.
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
219
220
221
222
223
224
225
227
228
229
230
231
232
233
234
235
236
237
238
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
268
269
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
288
289
290
291
292
293
294
295
296
297
298
299
300
306
307
308
311
312
313
314
315
316
317
318
319
320
321
322
325
326
327
328
329
340
341
342
343
344
345
345
346
347
348
349
350
351
352
353
354
359
363
364
366
367
375
376
384
385
386
387
388
389
390
391
392
393
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
424
428
426
427
428
429
430
431
432
433

## Strategic Planning Delivery & C
Todays Date = |  | 2025-06-26 14:29
Meeting Date | ID Number | Who Added | ACTION | Agenda Item | Status | Who is Actioning | B/F Date | Completion Date | Update (To be completed by Actioner) | Evidence/Rationale (To be completed by Actioner)
27.10.2022 | 1 | AM | Terms of Reference LB requested following the workshop session can these be brought back for assurance, these will need to be reviewed frequently. | 3 | Complete | AM / G Black |  | 26.01.2023 | Update 27.10.2022 - ToR were presented at the next meeting on the 26.01.2023 for approval
27.10.2022 | 2 | AM | Terms of Reference DR will meet with A Warrick to review and discuss the forward planning for the Committee. | 3 | Complete | DR |  | 26.01.2023 | Update 27.10.2022 - DR drafted a forward plan and presented it at the meeting next meeting.
26.01.2023 | 3 | AM | Terms of Reference DR highlighted to members an agreement was made to include an Independent Sector Representative in the Advisory Members, a discussion was had with J Gatherum and AM will amend the Terms of Reference to suit. | 4 | Complete | AM |  | 26.01.2023 | Update 26.01.2023 - AM shared invites with J Gatherum
26.01.2023 | 4 | AM | Strategic Planning Group Update GBl requested that a forward workplan for the SPG is shared at the next Committee meeting. It was proposed and agreed that this would be a standing agenda item. | 6 | Complete | AM | 27.04.2023 |  | Update 30.01.2023 - AM included on the next Agenda / Agenda Planner
26.01.2023 | 5 | AM | Areas of service change or commissioning suggested by the IJB Annual Performance Report 2021/22 Furthermore the Committee seeks guidance from JW and DR on the proposed outcome. Originally a Decision was sought to recommend IJB place Directions on the Partnership to progress areas, however the Committee reflected that as there is no information on impact of progressing specific areas its Decision would be limited to requesting that specific areas of work are scoped before a Decision on a Direction could be taken. | 7 | Complete | AA |  | 26.10.2023 | Update 26.10.2023 - Donna Maxwell presented the IJB Annual Performance Report 2022 / 2023 Priorities for Future Action on behalf of Ananda Allan
26.01.2023 | 6 | AM | Carers Act Funding JW also reiterated that these reports should go via Health and Social Care Leadership Group first for Governance Purposes. VG will share this with the H&SCLG. | 9 | Complete | VG |  | 23.03.2023 | VG completed an updated report to go to the IJB on 23.03.2023
26.10.2023 | 7 | AM | 2022 / 2023 Annual Delivery Plan Update DR mentioned the table within 3.6 it highlights the actions. JW asked in terms of taking this into the Local Authorities bring together Partners. DR will work with K Armstrong. | 10 | Complete | DR |  | 15.04.2024 | Update 26.10.2023 - This has not gone throught the Local Authority Route, this will follow on from the ADP submission on 27.10.2023 Update 14.02.2024 - DR confirmed there is an update on Directions to SW Committee today but we haven't taken a version of this report through that route yet. My plan would be to take it when the Q4 Update is ready - likely the end of May 2024 Update 15.04.2024 - Progress against Directions was taken to SW Committee in February has also gone to the IJB and also NHS Board.
16.05.2023 | 8 | AM | Update from the Strategic Planning Group Action: AM will share the workplan for the Strategic Planning Group and the Presentation given to the NHS Board. The Workplan that was shared was discussed with CB and DR and links with the Agenda Matrix for this committee. | 5 | Complete | AM / CB |  | 26.10.2023 | Update 16.05.2023 - AM shared the documents with the draft notes but this will come back formally to the next committee. Update 26.10.2023 - CB updated on this within her update on The Strategic Planning Group
16.05.2023 | 9 | AM | Commission and Process for Developing the 2023 / 2024 Annual Delivery Plan and 2023 / 2026 Medium Term Plan Action: Finalised Annual Delivery Plan and Medium Term Plan to come back to the next committee in July. | 8 | Complete |  | 27.07.2023 |  | Update 16.05.2023 - AM added to rolling agenda for K Armstrong to bring this back
27.07.2023 | 10 | AM | Draft Minutes of the Meeting of 26th January and 16th May 2023. Action: An email is to be issued to voting members present at the meeting on the 26th January 2023 seeking approval of the minutes and Vice Chair to be contacted for approval of the minutes from the 16th May 2023. Action: From the minutes on the 16th May and the update in relation to extraordinary meetings around Right Care, Right Place, JG asked if there was an opportunity for a member from the Independent Sector to attend the extraordinary meetings. DR agreed to check attendance at those meetings and let JG know. | 3 | Complete | AM / DR |  | 09.08.2023 | Update 09.08.2023 - AM emailed out the previous notes, where P Stevenson / G Black confirmed approval Update 18.08.2023 - IE / AM issued J Gatherum with an update from DR following his request
27.07.2023 | 11 | AM | Update from the Strategic Planning Group Action: JG asked if the SPG are satisfied with the level of engagement with Care Home providers in relation to Right Care, Right Place given the potential impact on their business and services they provide. DR advised it is an important element and cannot comment on whether or not the SPG are satisfied with the level of engagement as DR was not at the last meeting and is not aware of asking that question to the SPG. DR agreed to check whether this was discussed and feedback to JG. DR assured members that we have sought to engage and will continue to seek to engage, there are meetings scheduled with a number of Providers and we continue to offer those meetings. | 5 | Complete | DR |  | 18.08.2023 | Update 18.08.2023 - As per above - DR issued info to Jim
27.07.2023 | 12 | AM | IJB Annual Performance Report 2022 / 2023 Acrion: JG noted a change in the report to recognise the National Care Home Contract (NCHC) has now been signed off. JG asked that the fact the NCHC has been signed off under severe regret and duress whether we are doing a disservice to the readers of their support without putting mention of that as it is not a normal year and may suggest that everything is business as usual. DR suggested the wording is rephrased to “the extended time taken to complete this year’s negotiations has highlighted to the IJB and the Partnership the pressures being faced by Care Homes across Scotland.” JG agreed with the rephrasing of the wording and AA to amend. Action: GB noted on page 5 towards the end under SCP it states “Strategic Commissioning Plan was approved by IJB... no review of SCP required.” AA highlighted it is a statutory requirement to comment on whether we have reviewed our SCP and it has to be reviewed once every 3 years. AA agreed to take this comment away to describe this in a better way. | 7 | Complete | AA |  | 27.07.2023 | Update 23.08.2023 - AA confirmed changes were made within the meeting, and document was published prior to 31st July - https://dghscp.co.uk/wp-content/uploads/2023/07/20230727-IJB-Annual-Report-22-23-FINAL-DRAFT.pdf
27.07.2023 | 13 | AM | 2022 / 2023 Annual Delivery Plan Quarter 4 Update Action: GB asked for reassurance to be sought from operational colleagues on the reasoning for going from a red to a suspension. DR agreed to go back to operational colleagues to ask that in future reporting we are much more explicit to differentiate between the reds and suspended and what triggers you going from a red to suspension. Members were supportive of this challenge going back to operational colleagues. Action: GB noted that endowment funding is being used for the good and important work around staff wellbeing however we cannot rely on endowments as this is normally approved annually. DR agreed to feedback into the reporting for the ADP 2023 / 2024 and highlight as one of the risks. Members agreed for this to be formalised as a risk. | 8 | Complete | DR |  | 26.10.2023 | Update 23.08.2023 - DR has gone back to Workforce Colleagues to ask that the use of endowment funding be highlighted as a risk - DR expect this to be reflected in the Q2 report. Update 24.10.2023 - K Armstrong confirmed: For clarity between what denotes a red graded action and a suspended action, we have defined a suspended action as follows - “Suspended - A conscious decision due to pressures on services to stop/halt the pursuit of a particular action, i.e. due to staff absence, reprioritisation of actions.” The definition of a red graded action as set out by SG continues to be "Unlikely to complete on time/meet target". This should help teams to differentiate between the two definitions. We will make reference to this in the next ADP paper to committee. In relation to the funding of the Staff Support Service, this action is currently not being monitored through the ADP process and instead forms part of the Workforce Plan Action Plan updates. This level of detail in terms of risk is not included within the action plan although, the funding risk was captured in the 2022/23 ADP albeit absent of mitigation. I contacted the Project Manager for Working Well Staff Support projects who confirmed that a paper is currently being drafted considering the options beyond March 2024 when the existing funding is due to end, and will be considered by the relevant committees/forums over the coming months.
27.07.2023 | 14 | AM | Dumfries and Galloway Alcohol and Drug Partnership Annual Reporting Survey 2022/23 Action: AMcF and GB advised that the committee would need to seek clarification from governance if this committee has authority to approve the survey. The committee agreed that it would make the Decision to recommend that the Annual Reporting Survey is approved but further clarification is to be sought if the committee can approve. AMcF agreed to follow up with KB for clarification on this matter and IE to respond to DG. | 10 | Complete | AMcF / KB / IE |  | 15.08.2023 | Update 15.08.2023 - JW met with V White, agreed for this to go for formal approval to the September IJB, AM linked with Deanne Gilbert and added to the Rolling Agenda Matrix
26.10.2023 | 15 | AM | Update from Strategic Planning Group Action: Notes from the 5th October meeting will be shared within the papers, following formal approval at the January meeting (11.01.2024) Action: Annual Report 2022 / 2023 to be produced | 5 | Complete | AM CB / KB | 2025 |  | Update 21.11.2023 - Notes have been shared, Annual Report still under discussion Update 16.01.2014 - CB / KB presented a presentation with the update / progress and an annual review will come back in 2025. They recognised that the Strategic Planning Group and this Committee would benefit from an aligned Annual Report for end 2023 - 2024. As the meetings previously for SPG was adhoc.
26.10.2023 | 16 | AM | IJB Annual Performance Report 2022 / 2023 Priorities for Future Action Action: AMcF agreed with the discussion and these should be picked up, and this links into the Right Care Right Place and respite care this should all be linked. The report is missing the increasing costs, and should highlight exactly what is increasing. Action: AMcF requested scheduling a workshop in January / February following publishing the Report for this Committee in terms of this discussion. Action: GB raised a concern in terms of the translation page to include Ukrainian. | 6 | Complete | AA / DM |  | 15.02.2024 | Update 15.02.2024 - Workshop is scheduled for March where V Gration will lead for all IJB Members in terms of RCRP AA confirmed Ukranian was added to the final report - CLOSED
26.10.2023 | 17 | AM | Acorn House / Short Break Services Update Action: Update to formally come via this committee prior to the IJB | 7 | Complete | AM |  | 16.01.2024 | Update 21.11.2023 - L Durrant confirmed she will be submitting a report and attending in January Update 16.01.2024 - Acorn House Report was shared and discussed withn an in committee session, a meeting will be held offline to discuss further options prior to going to the IJB in March, AM will schedule this meeting - Meeting was scheduled and held on 24.01.2024
26.10.2023 | 18 | AM | Update on Mental Health Strategy Action: GB thanked JM for setting the context and for highlighting the success and challenges. KB has discussed with JM in regards to the New Mental Health Strategy is released we must support the delivery of this strategy through this Matrix. KB mentioned this will be updated approx | 8 | Ongoing | JM / KB | 22.07.2025 |  | Update 28.08.2024 - AM linked with KB again for an update. Update 14.11.2024 - Members agreed this is required to come back in January, KB will link with J Murray again as we must understand our gaps. Update 21.01.2025 - KB highlighted this is still ongoing and will be picked up in terms of reporting / governance of this at HSCLG on 23.01.2025 and will be brought back. Update 22.04.2025 - G Marr mentioned an element of confusion in terms of this, and GM has requested for a Localised Strategy based on the National Strategy and this will come to the next meeting, VG agreed to also support this.
26.10.2023 | 19 | AM | Non Registered Third Sector Contracts Action: CB supported the piece of work in terms of the Third Sector, there will be organisations out there that will have a contract, but will have sensitive issues who have relied on the funding. If any support is needed in terms of support / conversation the Third Sector would be supportive of this. SW is due to link regarding the support for the future. | 9 | Complete | SW / CB |  | 15.04.2024 | Update 21.11.2023 - CB and S Walker have met and agreed a plan of action to support third sector organisations through this piece of work; this will include a dedicated TS forum event focussing on procurement and access to a programme of training and support in the new year. Update 16.01.2024 - DR confirmed this needs to go through procurement process and will come back. Update 21.02.2024 - CB will pick this up within the meeting. Update 15.04.2024 - SW confirmed communications continue with Third Sector
26.10.2023 | 20 | AM | Carers Strategy Delivery Plan Action: RDMc updated members of her own lived experience, and without unpaid carers her life would be impacted significantly, VG will link with RDMc in terms of her unpaid carers. | 10 | Complete | VG |  | 16.01.2024 | Update 18.12.2023 - VG has arranged a meeting for the 11th January 2024. Update 16.01.2024 - VG and Rhianna have met, and have confirmed to involve her carers.
26.10.2023 | 21 | AM | Care and Support at Home: Older People Action: Recommendation Wording to be reviewed | 12 | Complete | KB |  | 23.04.2024 | Update 08.01.2024 - This will be picked up at the joint IJB Chair / Vice Chair session on the 25.01.2024 Update 16.01.2024 - KB confirmed this will be picked up with the IJB Chairs / Vice Chairs at the session on the 25.01.2024 - GB has noted his apologies at this session. KB mentioned this is an assurance committee it does not approve anythig. Update 23.04.2024 - KB / GB has discussed this in numerous forums, recommendations will be made clear in reports and picked up within Governance Review of Reports.
16.01.2023 | 22 | AM | Update from the Strategic Planning Group Action: CB confirmed the Committee will receive the Terms of Reference for approval / comments. | 5 | Complete | CB / AM |  | 23.04.2024 | Update 16.01.2024 - These will come to the committee in April Update 23.04.2024 - ToR were presented in Committee today and was approved to go to the IJB for formal approval, work will continue in terms of Membership.
16.01.2023 | 23 | AM | Performance Measures / Workshop Update Action: RA is meeting next week with Mike Shepley, Head of People and Transformation to discuss where Social Work / Wider Partnership are in terms of options for putting forward ideas. RA is keen for EM to also be invited. | 6 | Complete | RA / EM |  | 17.01.2024 | Update 17.01.2024 - RA confirmed invite was shared for E Macleod to attend
16.01.2023 | 24 | AM | Committee / SPG workshop on the Annual Delivery Plan Workshop to be arranged in March, AM will look into arranging. | 9 | Complete | AM / DR |  | 25.01.2024 | Update18.01.2024 - AM emailed IJB Chair for approval of the 19.03.2024 prior to issuing invite Update 25.01.2024 - Confirmed for Tues 19th March and issued to all IJB Members.
23.04.2024 | 25 | AM | Strategic Planning Group Review of Terms of Reference / Formal Update Action: AW echoed the discussion and is supportive to link with CB in terms of the discussions, in terms of possible barriers. Action: Recruitment processes have been discussed and are being reviewed at the moment, once finalised AW will share these round members. | 6 | Complete | HG / CB |  |  | Update 28.08.2024 - AM linked with H Green / C Brown for an update.
23.07.2024 | 26 | AM | Strategic Planning Group Update AMcF raised some questions in terms of the Planning People Guidance, DR will link direct with R Edgar and feedback. | 5 | Complete | DR / RE / AMcF |  | 24.07.2024 | Update 24.07.2024 - RE confirmed and update in terms of AMcF questions re HIS and DR will feedback
23.07.2024 | 27 | AM | Strategic Needs Assessment Update Action: DR mentioned he would link with A Allan out with in terms of a workshop early Autumn to discuss the Priority Areas / Feedback from Strategic Planning Group, to allow development. AMcF as IJB Chair supported this approach. | 6 | Complete |  |  | 31.07.2024 | Update 31.07.2024 - AM has issued an invite for a Workshop on the Joint Strategic Needs Assessment and also the feedback from Strategic Planning Group. Update 06.08.2024 - Confirmed for 19th Nov and in the IJB Members diary.
23.07.2024 | 28 | AM | Supported Accommodation Opportunity Garrick Site, Stranraer Action: Members approved the discussion and for GB to formalise a direction to be provided to the Local Authority. | 10 | Complete | GB / KB |  | 14.11.2024 | Update 28.08.2024 - AM linked with GB / KB for an update. Update 14.11.2024 - DR confirmed a direction is going to the December IJB and will go as appendix with G Blacks Committee Update
14.11.2024 | 29 | AM | Strategic Planning Group Update Action: KB will pick up the SW Visioning Piece, and this will be developed and brought to a future IJB Meeting. | 6 | Complete | KB | 22.04.2025 |  | Update17.12.2024 - KB issued direction for SW Visioning for Members to approve which a reminder was issued at the IJB Meeting, report on SW Visioning will come back to the next Committee. Update 21.01.2025 - Social Work Visioning Paper due to come back to the next committee lead by N Hamlet / D Rowland
14.11.2024 | 30 | AM | Proposed Priorities Arising from Review of the Annual Performance Report Action: A confirmed once we capture everything, we can then formalise what we have in place. AA will link with KB outwith. AMcF mentioned it does benefit the IJB to receive an update on all the directions. | 8 | Complete | AA / KB | 14.01.2025 |  | Update 09.01.2025 - IJB Direction Workshop scheduled for Tuesday 14th January 2025 further feedback will be highlighted at January committee.
21.01.2025 | 31 | AM | Review of the Strategic Commissioning Plan Action: A discussion was had with a number of members where they agreed a further amendment to Strategic Commissioning Intention 9 to read, ‘allocate funding where there is greatest need and priority.’ This was following a comment FK provided. KW will review this and amend. | 7 | Complete | KW |  | 04.03.2025 | This will be amended and in the final draft which will go to the March IJB.
21.01.2025 | 32 | AM | Carers Strategy Delivery Plan Action: CB mentioned in terms of the process in coming back to the Strategic Planning Group, timings would be a concern, DR / KB agreed the requirement to have this as a separate item at the IJB on the 4th March 2025, where CB would attend and provide the Strategic Planning Groups views, similar to the RCRP IJB in October 2024. | 8 | Complete | AM / KB |  | 04.03.2025 | Update 03.04.2025 - E Forsyth attended the IJB on the 4th to present the Carers Strategy Delivery Plan, where all comments were noted and recommendations were approved as appropriate.
21.01.2025 | 33 | AM | Health and Social Care Workforce Plan Update Action: PJ will share the response to Scottish Government, for AM to share with committee members. | 10 | Complete | PJ / AM |  | 10.06.2025 | Update 10.06.2025 - AM sent Workforce Plan from NHS Dumfries and Galloway which was approved at our Staff Governance Committee on Monday 24th March 202, this was submitted to Scottish Governkment on 26.03.2025
22.04.2025 | 34 | AM | Long Term Conditions and Rehab Alliance Update Action EB thanked members for the discussion and declared an interest and mentioned we are missing something in terms of Managed Clinical Networks and fully supports from a clinical level, but further work is required in terms of a steering group. KB will link in terms of a meeting with networks. | 8 | Complete | KB |  | 10.06.2025 | Update 10.06.2025 - KB confirmed she has BST member working on this and all linkages are being made.
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
219
220
221
222
223
224
225
227
228
229
230
231
232
233
234
235
236
237
238
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
268
269
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
288
289
290
291
292
293
294
295
296
297
298
299
300
306
307
308
311
312
313
314
315
316
317
318
319
320
321
322
325
326
327
328
329
340
341
342
343
344
345
345
346
347
348
349
350
351
352
353
354
359
363
364
366
367
375
376
384
385
386
387
388
389
390
391
392
393
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
424
428
426
427
428
429
430
431
432
433

## Transformation Innovation & Del
Todays Date = |  | 2025-06-26 14:29
Meeting Date | ID Number | Who Added | ACTION | Agenda Item | Status | Who is Actioning | B/F Date | Completion Date | Update (To be completed by Actioner) | Evidence/Rationale (To be completed by Actioner)
10.11.2022 | 1 | AM | Committee Terms of Reference VW asked for GM, DR and LD to link prior to the workshop to discuss the requirements. | 3 | Complete | AM |  | 20.04.2023
09.02.2023 | 2 | AM | Ophthalmology Redesign Project Charter CA confirmed this is a 3-5 year programme, which will also include developing the Team and Staff Members. CA will pick up following this meeting regarding the EQIA. Members agreed that we develop a Direction to the IJB, delivery of this will be monitored around the IJB Finance, Performance and Quality Committee, DR will link with CA prior to taking this to the IJB in March 2023. | 6 | Complete | CA DR / CA |  | 21.08.2023 | Update 14.03.2023 - DR / CA agreed that Dianne will support Callum in developing a short paper to IJB on the planned change in the model of care for Ophthalmology, which will incorporate a Direction to implement the change. Update 27.06.2023 - Direction is being developed and will come to the next committee in August Update 21.08.2023 - NH confirmed this no longer needs to go for a Direction so can be closed off the matrix
09.02.2023 | 3 | AM | Primary Care Transformation Plan Update NN highlighted there has been significant progress, but Third Sector colleagues still struggle to participate fully in exploring opportunities to organise care and support differently due to concerns about confidentiality, GB will invite NN to the next Contract Development Group. | 7 | Complete | GB |  | 03.05.2024 | Update 26.06.2023 - NN confirmed conversations are ongoing with Kate Gribbons, following Niomi and Lisa linking. Update 13.11.2023 - NN confimed no progress since the last update due to staff pressures / sickness this will be picked up by TSDG in the New Year Update 03.05.2024 - NN attended the Contract Development Group but conversations about providing care differently have ceased. TSDG no longer involved in these conversations Update 06.06.2024 -AWebb mentioned re the above update that he would follow this up and he confirmed: Third Sector are very willing and interested in engaging with the work outlined. Historically the team have been involved in the relevant groups and conversations. I’m told this stopped as either the meetings have ceased or we are no longer invited, not because we have withdrawn. So, however we have gotten to this position, I would like to reiterate our commitment to being involved. The team would welcome invites to the relevant forum and will attend wherever/whenever we can.
09.02.2023 | 4 | AM | Future Plans for this Committee DR previously had a conversation regarding the future, beyond the system pressures and this committee require looking at the key themes which will then be included in the Strategic Commissioning Intentions. Horizon Planning Papers to come via this committee. DR will link with AM and VG out with this meeting regarding Horizon Planning. | 10 | Complete | DR |  | 28.02.2023 | Update 09.02.2023 - DR requested a meeting with VG and AM for Tues 28.02.2023 - Horizon Plans will be included in the Agenda Matrix
11.05.2023 | 5 | AM | Primary Care Transformation Programme Board Update Action: IC requested for a formal update to come back to the next committee. | 5 | Complete | GB |  | 16.11.2023
11.05.2023 | 6 | AM | Workshop Session – What the Data is Telling us? VG confirmed the process going forward is for IC, RDMc, DR and VG to link regarding the way forward. VG will schedule this. | 7 | Complete | DR |  | 16.11.2023
10.08.2023 | 7 | AM | Maternity Service Update - Wigtownshire Agreed that a paper be brought back to IJB to inform of the outcome of the Consultation. | 5 | Complete | AM |  | 23.08.2023 | Update 23.08.2023 - AM linked with Justine / L Boyce to check which IJB this year it is coming to, for it to be added to the rolling agenda Matrix
10.08.2023 | 8 | AM | Short Break Services Update Written update to be brought through an IJB Committee | 6 | Complete | AM |  | 23.08.2023 | Update 23.08.2023 - AM linked with Justine / S Morgan & F Paton, to confirmt this will come to the IJB Strategic Planning & Commissioning Committee on 26th October 2023, added to the Rolling Agenda Matrix
10.08.2023 | 9 | AM | Draft Complex Needs Plan Approved that on completion of ongoing engagement in August the final Complex Needs Plan 2023-2026 and accompanying draft implementation plan is presented to the IJB for final approval in September. | 7 | Complete | AM |  | 23.08.2023 | Update 23.08.2023 - AM added this to the IJB Rolling Agenda Matrix for September IJB
10.08.2023 | 10 | AM | Director of Public Health Annual Report 2022 / 2023 Agreed that the Committee would like to be kept informed of progress in light of this report. | 9 | Complete | VW |  | 18.02.2025 | Update 23.08.2023 - AM emailed VW to check how regular this will be reported, and for it to go on the Rolling agenda Update 16.11.2023 - VW completes an Annual Report, once a year and will share it next year. Update 13.08.2024 - VW confirmed this will come to the first committee in Jan / Feb 2025 Update 10.01.2025 - VW asked to remove this at this stage due to not having one to discuss but will update on the Scottish Government Population Health Frameworkat the next meeting. Update 18.02.2025 - VW confirmed this is not a statutory requirement but when completed this will come back.
16.11.2023 | 11 | AM | Primary Care Transformation Update Action: VW confirmed a report is going to Public Health Committee regarding Population Health and Health Inequalities, which will then be submitted to this committee. We must be going to the IJB regarding the focus on Prevention and Early intervention, to transform the system we must be included more. Action: GB will bring back an update to this committee in regards to Sustainability and to agree as a Partnership how we support the new model. | 5 | Complete | VW GB |  | 14.05.2024 | Update 24.05.2024 - AM shared the paper for comments to all members.
16.11.2023 | 12 | AM | Dental Services to be brought back to this committee in a similar approach as the above. | 5 | Complete | DR |  | 13.02.2024 | Update 13.02.2024 - Presentation was provided to members at the February Committee
16.11.2023 | 13 | AM | Workshop Session – Digital Session – Lead by Viv Gration and Euan MacLeod Action: Progress on the 4 questions highlighted by DR to be brought back following discussion within the Digital Transformation Programme Board. | 8 | Complete | DR |  | 14.05.2024 | Update 13.02.2024 - DR confimed the 4 questions were agreed and have been encorporated into a delivery plan, First draft of delivery plan to be shared by the end of March, then will come back to this committee, this is to be moved at pace and scale. DR also confirmed this action will be complete following the next Committee in May. Update 14.05.2024 - VG presented the Digital Delivery Plan on behalf of E MacLeod and this update was within.
14.05.2024 | 14 | AM | Galloway Community Hospital Review Update Action: Members discussed the communication approach. CH highlighted this is her Ward, and agreed in terms of the positive messaging that is needed and also open conversation the Community to support moving forward. CH confirmed she is happy to be involved in this process / support. | 6 | Complete | RE / CH |  | 13.08.2024
20.05.2025 | 15 | AM | Strategic Decisions Action: Agreed to propose that IJB Members participate in a workshop in August 2025 to explore these pathways and hear people’s experiences with a view to agreeing a Direction to redefine how we provide support to those in greatest need. | 6 | Complete |  |  | 03.06.2025 | Update 03.06.2025 - Agreed at IJB to hold this workshop following the September IJB, AM issued diary invite.
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
219
220
221
222
223
224
225
227
228
229
230
231
232
233
234
235
236
237
238
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
268
269
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
288
289
290
291
292
293
294
295
296
297
298
299
300
306
307
308
311
312
313
314
315
316
317
318
319
320
321
322
325
326
327
328
329
340
341
342
343
344
345
345
346
347
348
349
350
351
352
353
354
359
363
364
366
367
375
376
384
385
386
387
388
389
390
391
392
393
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
424
428
426
427
428
429
430
431
432
433

## IJB Agenda Matrix 2025
IJB Meeting Sates | Agenda Headings | Agenda Items
Tuesday 4th March 2025 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
Committee Updates x 4
| Governance | Directions (new draft Directions) - maternity and short breaks updates
Paper on Chair and Vice Chair - members incl. Carer and Service Rep
Performance
GP Sustainability Plan (following visioning paper)
Carers Delivery Plan
Right Care, Right Place x 4
Strategic Commissioning Plan - 2025-2028
Finance
IJB Meeting Sates | Agenda Headings | Agenda Items
Tuesday 3rd June 2025 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
Governance
Direction Update
Scheme of Integration Update
Performance
GMS - Building a New Future Together: Shaping the Future of General Medical Services in Dumfries and Galloway - D Rowland / G Bell
Unscheduled Care Update - G Marr / K Bell
Adult Visioning Update - G Marr
Third Sector Commissioning - Prioritisation - V Gration
| Finance | Draft Accounts
IJB Meeting Sates | Agenda Headings | Agenda Items
Tuesday 23rd September 2025 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
| Governance | Scheme of Delegation - K Bell
Membership Update - K Bell
| Performance | RCRP / Community Hubs / Flexible Beds Update - S Mottram
Annual Performance Report - Final Sign Off - Ananda Allan
Finance
Approval of Annual Financial Report and Accounts
| Workshop | Strategic Decisions
IJB Meeting Sates | Agenda Headings | Agenda Items
Tuesday 16th December 2025 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
2026 IJB Meeting / Committee Dates
| Governance | Direction Performance
Performance
Finance

## Committee Agenda Matrix 2025
Committee Meetings | Agenda Headings | 25th February 2025 | 24th June 2025 | 16th September 2025 | 18th November 2025
Audit, Risk and Governance |  |  |  | IJB Governance Statement 2024 / 2025
|  |  | Internal Audit Report – Care and Support at Home - Richard Fox | Internal Audit Report – Care and Support at Home - Richard Fox
|  |  | Best Value Statement - Kirsty Bell | IJB Risk Update - K Bell | IJB Risk Update - K Bell
|  |  | Risk Update - Kirsty Bell |  | Annual Report - Freedom of Information
| Governance | External Audit Plan 24/25 | MOU and ISA - Nicole Hamlet |  | Annual Report - Chief Social Officer
|  | Chief Internal Auditor Quarterly Update | Scheme of Delegation |  | Annual Report - Healthcare Governance Assurance Report
|  |  | Chief Internal Auditor Quarterly Update | Chief Internal Auditor Quarterly Update | Chief Internal Auditor Quarterly Update
|  | 7th January 2025 | 8th April 2025 | 8th July 2025 | 7th October 2025
Finance, Performance & Quality |  |  | Financial Update - K Kerr
|  |  | Direction Performance Update - Kirsty Bell | Remote & Rural - D Rowland
|  |  |  | Strategies - Cancer. MH & Palliative Care - K Bell | Service Reviews - K Bell
| Finance |  |  | Financial Update - K Kerr | Financial Update - K Kerr
|  | Direction Performance Update - Kirsty Bell |  | SW Savings Update - G Marr (action from IJB 03.06.2025)
| Performance | Contract Monitoring Update - Peggy Taylor |  | Direction Performance Update - Maternity / RCRP Flexible Beds - Kirsty Bell | Direction Performance Update - Kirsty Bell
| Quality Assurance | Transport Update - David B
|  | Quarterly Community Planning Partnership Performance update - Andy McFarlane |  | Galloway Community Hospital Review Update - C Ambridge
Flexible Bed Update - Euan MacLeod
|  | 21st January 2025 | 22nd April 2025 | 22nd July 2025 | 21st October 2025 | January 2025
Strategic Plan Delivery and Commissioning | Strategic Needs Assessment
| Strategic Planning Group | Monthly Update - C Brown |  | Quarterly Update - F Kane
Service Reviews - K Bell
| Planning Priorities |  | Strategies - Cancer, MH & Palliative Care - K Bell | Strategies - Cancer & Palliative Care - K Bell
Mental Health Local Strategy - J Murray
| Commissioning Plan | Carers Delivery Plan - L Forsyth | SW Visioning Piece - N Hamlet / D Rowland | Annual Performance Report - Final Sign Off - Ananda Allan | Third Sector Prioritisation - V Gration / S Walker
|  | Palliative Care Strategy - G Coupland / K Bell |  | Health and Social Care Renewal - D Rowland
Carers Delivery Plan - V Gration / S Abbott
|  | Update on SCP Refresh - K Willacy | Long Term Conditions and Rehab Alliance - K Bell / G Coupland
| Directions Setting | ADP 2025/26 - K Willacy | GMS - Building a New Future Together: Shaping the Future of General Medical Services in Dumfries and Galloway - D Rowland / G Bell / L Bunney / L Kirkpatrick / G Coupland
Remote & Rural - D Rowland
Quarterly Update - P Jamieson
| Workforce Plan |  |  | Quarterly Update - M Shrimpton / Pam Jamieson
|  | 18th February 2025 | 20th May 2025 | 19th August 2025 | 25th November 2025 | Feb 2025
Transformation, Innovation and Delivery | Sustainability and Modernisation | Planned Financial Recovery Actions for 2025/26 - Katy and Kirsty | USC Review - Kirsty Bell / Gareth Marr
Strategic Decisions - David Rowland
| Population Health | LOIP Update - A McFarlane
SG Population Health Framework - Valerie White
Partnership and Collaboration
Progress Report on Agreed Actions to Improve - Effectiveness of Integration - Ananda and Viv
| Health Inequalities Outcome and Inclusion | Specific Duty Reporting Timeline - L Fitzpatrick
| Engagement and Participation | Quarterly Report - Rod
Strategic Needs Assessment
| Workshop Sessions | Place Based Planning - Euan M

## IJB Agenda Matrix 2024
IJB Meeting Sates | Agenda Headings | Agenda Items
Wed 26th April 2023 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
Membership Update
| Governance | N/A
| Performance | Maternity Service Update
| Finance | Draft Financial Paper
IJB Meeting Sates | Agenda Headings | Agenda Items
Thursday 22nd June 2023 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
| Governance | Integration Scheme
Governance Procedure (Recording, Monitoring & Managing Directions)
Direction Performance
| Performance | IJB Committees Minutes / Verbal Updates
Short Break Service Report (Following IJB P,F & G Committee 13.04.2023)
| Finance | Draft Accounts
IJB Meeting Sates | Agenda Headings | Agenda Items
Wednesday 27th September 2023 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
| Governance | Approval of IJB Standing Orders
Direction Performance (closure of Direction IJBD1702, IJBD1901, IJBD2110, IJBD 1802 and IJBD1705)
| Performance | IJB Committees Minutes / Verbal Updates
Right Care Right Place, Intermediate Care
Dumfries and Galloway Alcohol and Drug Partnership Annual Reporting Survey 2022/23
Draft Complex Needs Plan
Maternity Service Update
| Finance | Approval of Annual Financial Report and Accounts
IJB Meeting Sates | Agenda Headings | Agenda Items
Thursday 7th December 2023 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
2024 IJB Meeting / Committee Dates
| Governance | Direction Performance
| Performance | IJB Committees Minutes / Verbal Updates
Annual Performance Report
| Finance | Finace Update
IJB Meeting Sates | Agenda Headings | Agenda Items
Tuesday 5th March 2024 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
| Governance | Direction Performance
| Performance | RCRP Year 1 Evaluation Report
IJB Committees Minutes / Verbal Updates
Short Break Service Update
Chief Social Work Report
Complex Care Year 1 Evaluation Report
| Finance | Finace Update
IJB Meeting Sates | Agenda Headings | Agenda Items
Tuesday 4th June 2024 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda (only action is update of member)
IJB Committees Minutes / Verbal Updates
| Governance | Direction Performance (Kirsty Bell / Ananda Allan)
Refreshed Commissioning Plan 2025 - 2028 (David Rowland / Viv Gration)
Membership Update (Alan Webb / Rhianna Davies McCrorie)
Process for Perm. Appointment of Chief Officer (Pam Jamieson)
Performance
Annual Delivery Plan (David Rowland / Kirsty Bell)
Annual Performance Report - Proposal Paper (Ananda Allan)
Plan to Update Housing with Care and Support Strategy (Glen Graham)
Right Care, Right Place - progress update (David Rowland / Viv Gration)
Maternity Services Outcome Paper (Lyn Durrant / Justine Parkinson)
Short Breaks Paper (Lyn Durrant / Justine Parkinson / Stephen Morgan)
Finance
Finance Update (Katy Kerr)
IJB Meeting Sates | Agenda Headings | Agenda Items
Tuesday 24th September 2024 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
| Governance | Direction Performance
Updated Policies
| Performance | IJB Committees Minutes / Verbal Updates
Maternity Services Outcome Paper (Lyn Durrant / Justine Parkinson)
Short Breaks Paper (Lyn Durrant / Justine Parkinson / Stephen Morgan)
Finance Update
| Workshop | Annual Performance Report
IJB Meeting Dates | Agenda Headings | Agenda Items
Tuesday 17th December 2024 | Standard Business | Welcome & Introduction
Declaration of Interest
Approval of Minutes
Action Plan / Rolling Agenda
| Governance | Direction Performance
IJB risk strategy - K Bell
| Performance | IJB Committees Minutes / Verbal Updates
Carers Strategy - Viv G
Winter Plan - Kirsty Bell
CSWO Report - S Morgan
| Finance | Finance Update

## Committee Agenda Matrix 2024
Committee Meetings | Agenda Headings | 2023-02-23 | 2023-06-08 | 2023-09-07 | 2023-11-30 | 22nd February 2024 | 18th June 2024 | 17th September 2024 | 19th November 2024
Audit, Risk and Governance |  |  |  | NHS A&R Assurance Statement |  | Draft External Audit Plan | Draft Annual Report and Accounts 2023/24 | NHS Audit and Risk Committee Annual Assurance Statement | Chief Social Work Officer Annual Report
|  | Draft External Audit Plan | Draft Annual Report & Accounts 2022/23 | Annual Report and Accounts | External audit update | Internal Audit Update | External Audit Plan | Internal Audit Annual Report | External Audit Update
|  | Annual Accounts timetable and plan | External Audit Plan 22/23 | Final IJB Governance Statement | Internal audit quarterly update | Governance Update | Internal Audit Quarterly Report | Governance Update in Workshop Protocl | Internal Audit Quarterly Report
|  | Internal audit quarterly update | Internal audit quarterly update | External audit annual report | Quarterly risk report | Chief Finance Officer Update | Governance Update (all refreshed policies to be brought through this Committee - Alison Warrick) | Final IJB Governance Statement | Governance Update
| TBC | Quarterly risk report | Quarterly risk report | Internal audit annual report | Governance update (to include a paper for assurance on Alcohol and Drug Partnership Governance) |  | Code of Conduct Update | External Audit Annual Report | Chief Finance Officer Update
|  | Chief Social Work Officer Report | Healthcare Governance Annual Report | Quarterly risk report |  |  |  | IJB Annual Report and Accounts | IJB ARG Meeting Dates 2025
|  | Draft Scheme of Delegation | Governance update | Governance update |  |  |  | IJB FOI Report | New Committee Format (David R)
|  |  |  | Best Value Update |  |  |  |  | Chief Social Work Officer’s Annual Report
|  | 2023-03-14 | 2023-04-13 | 2023-07-05 | 2023-10-12 | 9th January 2024 | 9th April 2024 | 9th July 2024 | 8th October 2024
Finance, Performance & Quality |  | Draft Financial Plan assumptions 2023/24 | Final Draft of Financial Plan 2023/24 | Financial recovery plan update | Latest financial forecast update |  | Quarterly Community Planning Partnership Performance update - discussion on approach of reporting | Quarterly Community Planning Partnership Performance update | Quarterly Community Planning Partnership Performance update
|  | Quarter three financial forecast including IJB reserve review |  | Performance Report on Directions - including specific update on IJBD2202 | Performance Report on Directions | Performance Report on Directions | Contract Monitoring Report - Care Homes (Peggy Taylor) | Finance Update
| TBC | Performance Report on Directions |  | Contract Monitoring/ Quality Assurance | Contract Monitoring/ Quality Assurance | Directions Update | Finance Update | Directions Update | Finance Update
|  | Contract Monitoring/ Quality Assurance |  |  | Annual Performance Report | Climate Change (Katy / David B) | Directions Update (Kirsty Bell / Donna Maxwell)- demostrate performance framework | Update on the work of Alcohol & Drug Partnership | Directions Update
|  |  | Short Break Services Report |  |  |  | Finance workshop being scheduled after the Committee | Update on child health as part of the Dumfries and Galloway Children’s Services Plan | Adult Social Care Inspections
Patient and Service User Feedback Annual Reports
[8 empty] | Contracts Monitoring Update - Third Sector | Contracts Monitoring Update - Care and Support at Home
|  |  |  | Third Sector Contract Monitoring report | Governance Structure for Contract Monitoring |  |  | Annual Performance Report | Integration Joint Boards' Finance and performance 2024 (K Kerr - 29.07.2024)
|  | 2023-01-26 | 2023-05-16 | 2023-07-27 | 2023-10-26 | 16th January 2024 | 23rd April 2024 | 23rd July 2024 | 29th October 2024 | January 2025
Strategic Plan Delivery and Commissioning | Strategic Needs Assessment | N/A | N/A | Strategic Needs Assessment | N/A | N/A | Strategic Needs Assessment Update |  | Strategic Needs Assessment - Progress Update and Presentation of Template Chapter - Ananda | Presentation of first set of Chapters - Ananda
| Strategic Planning Group | Verbal Update | Verbal Update & Forward Workplan for SPG | Last months b/f | SPG Annual Report | Review of Membership / ToR Annual Report for 2022 / 2023 |  |  | SPG - Report from Group - Claire | SPG - Report from Group - Claire
| Planning Priorities | Review of Annual Performance Report and agreement of Priorities for Review / New Direction | Right Care Right Place Consultation Schedule | N/A | Review of Annual Performance Report and agreement of Priorities for Review / New Direction | Verbal update on Performance Measures / Workshop | RCRP - Future use of Cottage Hospitals | Annual Performance Report - Final Sign Off - Ananda Allan | Proposed Priorities Arising from Review of the Annual Performance Report - Ananda, Kirsty and Viv | Proposed Priorities Arising from First Chapters of JSNA - Ananda, Kirsty and Viv
|  |  | Month 3 Evaluation of Care and Support at Home Test of Change |  | Recommendations from APR Priorities for Review | Acorn House / Short Break Service Update | Maternity Consultation | Non-registered services procurement plan / Update - Sharon Walker - Deferred from April | Regional Planning Priorities - David R | Non-registered services procurement plan / Update - Sharon Walker
|  |  | Commission and Process for Developing the Annual Delivery Plan |  | Acorn House / Short Break Service Update |  | Carers Delivery Plan
[7 empty] | Advocacy Plan |  |  | Long Term Conditions and Rehab Alliance - Gillian Coupland / Kirsty Bell
Plan to Update Housing with Care and Support Strategy
Future GMS Service Profile PID
| Commissioning Plan | Care Home Commissioning Plan and Ownership Model | N/A | 2022/23 ADP | N/A | Latest Guidance on Strategic Commissioning Plan / Refresh | Annual Delivery Plan
|  | Carers Funding Proposals / Update Direction 1703 including Delivery of Carers Strategy / Plan |  | Draft IJB Annual Performance Report |  |  | Refreshed Strategic Commissioning Plan |  | Update on Progress with Refresh of the Strategic Commissioning Plan - Kerry W | Presentation of Draft Refreshed SCP - Kerry W
| Directions Setting | Paper introducing ADP linked to SCIs and Directions with Assessment of Direction Gaps and Proposed Directions | N/A |  |  | 2023/24 ADP Q2 Progress Report |  |  | Carers Strategy - Viv G
SCP Year 1 Delivery Report - Ananda
|  |  |  | ADP Annual Performance Report - Committee to reflect / directions | Update on Mental Health Strategy and LD Strategy - position paper following leadership meeting on 19th October 2023, then into NHS Board | Galloway Community Hospital - Major Service Change Progress Report and Recommendations |  |  | Analysis of Alignment of Directions to Strategic Commissioning Intentions - Ananda, Kirsty and Viv | Analysis of Alignment of Directions to Strategic Commissioning Intentions - Ananda, Kirsty and Viv
[5 empty] | Non Registered Third Sector Contracts |  |  |  | Recommended Additional Directions Arising from Analysis and Agreed Planning Priorities - Kirsty | Recommended Additional Directions Arising from Analysis and Agreed Planning Priorities - Kirsty
| Workforce Plan | N/A | N/A | N/A | Workforce Plan Annual Report | N/A |  |  | Review of Progress Against the Workforce Plan - Tracey's replacement | Review of Progress Against the Workforce Plan - Tracey's replacement
|  | 2023-02-09 | 2023-05-11 | 2023-08-10 | 2023-11-16 | 13th February 2024 | 14th May 2024 | 13th August 2024 | 12th November 2024 | Feb 2025
Transformation, Innovation and Delivery | Sustainability and Modernisation | Right Care, Right Place Participation and Engagement Proposals | Primary Care Transformation Plan (2023/24) | Right Care, Right Place Final Proposals | Proposal for Major Service Change 2 | Proposal for Major Service Change 3 | Strategic Needs Assessment |  | Proposed Financial Recovery Actions for 2025/26 - Katy and Kirsty | Planned Financial Recovery Actions for 2025/26 - Katy and Kirsty
|  | Ophthalmology Redesign Project Charter | Report-Out from Lens Ideas Development with Third / Independent Sector | Digital Programme Board Workplan aligned to National Digital Strategy | Proposal for Digital Transformation 2 | Proposal for Digital Transformation 3 | GCH Update on PID - Callum / Viv |  | Report on Progress with the National Remote, Rural and Island Framework - David R and Gill | Digital Future Planning - Kirsty
|  | Complex Care Programme Board Workplan and Recommendations |  |  |  | Primary Care Transformation Plan 2024/25 | Future GMS Service Profile PID |  | LENS Evaluation
|  | Primary Care Transformation Plan Update |  | Short Break Services & Maternity Services |  | Workplan for Major Service Change / Vision for DGRI |  |  | Digital Delivery Plan Progress Update - Kirsty
Digital Transformation…. E MacLeod
| Population Health | N/A | N/A | Annual Population Health Report | Primary Care Update - Grecy Bell | Dental Services Plan |  |  | Report on Update - Valerie W | N/A
Health Inequalities Report
| Partnership and Collaboration | N/A | Annual Report on Effectiveness of Integration | N/A | N/A | N/A |  |  | Assessment of the Effectiveness of Integration and Proposed Actions - Ananda and Viv | Progress Report on Agreed Actions to Improve - Effectiveness of Integration - Ananda and Viv
| Health Inequalities Outcome and Inclusion | Bi-Annual Report on Meeting Specific Duty Legislation |  |  |  | Review Relevant Indicators in Relation to Tackling Inequalities |  |  | Presentation of LOIP Actions and Progress - Valerie W | Presentation of LOIP Actions and Progress - Valerie W
| Engagement and Participation | N/A (Strategy Just approved Dec 2022) | Quarterly Assurance Report | Quarterly Assurance Report | Quarterly Assurance Report | Annual Report |  | Quarterly Report | Quarterly Report - Rod | Quarterly Report - Rod
| Strategic Needs Assessment | N/A | N/A | N/A | N/A | N/A
| Workshop Sessions - Horizon Scanning | N/A | What the data is telling us? | Opportunities in Technology | Digital Session | New and Innovative Ways of Care and Support | Workforce Development |  |  | Place Based Planning - Euan M